## Timeline
Week | Tasks to be Completed
1 | Finalise research objectives. Refine literature review.
2 | Gather the life assurance policy application dataset. Preprocess the dataset, handle missing values, and perform data cleansing. Conduct exploratory data analysis to gain initial insights.
3 | Identify highly correlated features and features with high feature importance scores. Conduct feature engineering to possibly create additional meaningful features. Split the dataset into training and testing sets.
4 | Develop and train supervised machine learning models using the training dataset. Experiment with different algorithms (logistic regression, decision trees, random forests, etc.) and hyperparameters. Evaluate the models using appropriate metrics (accuracy, precision, recall, F1-score) on the testing dataset.
5 | Finalise the development of the artefact (supervised machine learning model). Manipulate highly correlated features and features with high feature importance scores in the experimental sample of life assurance applications. Compare the classification results of the manipulated sample to the control group using the developed models.
6 | Analyse and interpret the experimental results. Conduct additional experiments and observations based on the identified factors influencing application conversion rates.
7 | Focus on write-up. If needed, refine the machine learning models based on the insights gained from experiments and observations. Fine-tune the models' hyperparameters to optimize their performance. Validate the models' generalizability by testing them on unseen data.
8 | Conduct a comprehensive analysis of the experimental and observational results. Interpret the findings, discuss the significance of the variables, and evaluate the overall performance of the models.
9 | Write the methodology section of the thesis, detailing the data collection process, preprocessing techniques, model development, experimentation, and observation approaches. Begin drafting the results and analysis section, summarising the key findings from the experiments and observations.
10 | Finalise the results and analysis section, including visualizations, tables, and statistical analyses. Write the discussion section, interpret the results, discuss their implications, and compare them to previous research. Start drafting the conclusion section, summarising the key findings, limitations, and recommendations for future research.
11 | Complete the writing of the conclusion section and revise the entire thesis. Proofread and edit the entire document for grammar, spelling, and formatting. Submit the completed thesis and prepare for the thesis defense.

## Experimental Design
Step | Description | Completed
Data Preparation | Collect and preprocess life assurance application dataset. | Y
Feature Selection | Conduct correlation analysis and calculate feature importances. Select top-n features.
Sample Selection | Implement stratified random sampling to create a representative sample.
Experimental Groups | Divide the sample into multiple groups, each representing a different ML model.
Model Training | Train each ML model using selected features and optimized hyperparameters.
Model Evaluation | Evaluate model performance on the training set using evaluation metrics.
Validation and Generalisation | Test models on unseen test set to assess generalisability.

## Experimental Plan
Objective | Tasks | Expected Outcomes
Feature Impact Analysis | Analyse experimental results to identify features with significant impact on application conversion. | Identify features consistently contributing to model accuracy.
Model Comparison and Selection | Compare performance of different ML models in predicting application conversion. | Identify models with highest accuracy and assess hyperparameter contribution.
Validation and Generalisation | Test selected models on unseen test set. | Assess generalisability and validate model performance.
Experiment | Description and Notes | Results
1 | Model: Logistic Regression
2 | Model: Decision Tree
3 | Model: Random Forest
4 | Model: Support Vector Machine
5 | Model: Neural Network
6 | Hyperparameter Tuning for Best Model
7 | Model Evaluation with Test Data
8 | Compare Model Performance and Select Best Model
9 | Refine Best Model and Feature Importance Analysis
10 | Validate Model on Unseen Data and Generalisation
11 | Interpretation of Model Results and Recommendations
12 | Finalise Experimental Report and Documentation